## Carpentry
Manpower Calculator- Shuttering Works
Sr No. | Formwork Item | Crew Size | Output in sqm/hr | Enter Qty for the day in sqm | Enter Working Hours per Day | Manpower required for the Day
[6 empty] | Carpenter | Helper
1 | Formwork to footings | 2 CARPENTERS, 1 HELPER | 1.2 |  |  | - | -
2 | Formwork to isolated footings | 2 CARPENTERS, 1 HELPER | 1.6 |  |  | - | -
3 | Formwork to rafts | 2 CARPENTERS, 1 HELPER | 1.4 |  |  | - | -
4 | Formwork to rafts D>0.75m | 2 CARPENTERS, 1 HELPER | 1.8 |  |  | - | -
5 | Formwork to tie beams | 2 CARPENTERS, 1 HELPER | 1 |  |  | - | -
6 | Formwork to high level tie beams D>0.45M | 2 CARPENTERS, 1 HELPER | 1.2 |  |  | - | -
7 | Formwork to Neck Columns | 2 CARPENTERS, 1 HELPER | 0.4 |  |  | - | -
8 | Formwork to U/G Water tank | 2 CARPENTERS, 1 HELPER | 0.6 |  |  | - | -
9 | Formwork to basement retaining walls | 2 CARPENTERS, 1 HELPER | 0.9 |  |  | - | -
10 | Formwork to columns (small size) | 2 CARPENTERS, 1 HELPER | 0.7 |  |  | - | -
11 | Formwork to Columns (large size) | 2 CARPENTERS, 1 HELPER | 0.9 |  |  | - | -
12 | Formwork to D/S beam internal (shallow) | 2 CARPENTERS, 1 HELPER | 0.6 |  |  | - | -
13 | Formwork to D/S beam external (Deep) | 2 CARPENTERS, 1 HELPER | 0.7 |  |  | - | -
14 | Formwork to D/S beam external (Shallow) | 2 CARPENTERS, 1 HELPER | 0.4 |  |  | - | -
15 | Formwork to D/S beam external (Deep) | 2 CARPENTERS, 1 HELPER | 0.6 |  |  | - | -
16 | Formwork to lift walls single core | 2 CARPENTERS, 1 HELPER | 0.6 |  |  | - | -
17 | Formwork to lift walls multi core | 2 CARPENTERS, 1 HELPER | 0.8 |  |  | - | -
18 | Formwork to slab decking (10ft) hourdi | 2 CARPENTERS, 1 HELPER | 1.6 |  |  | - | -
19 | Formwork to slab decking (>10ft) hourdi D/S beams | 2 CARPENTERS, 1 HELPER | 1.2 |  |  | - | -
20 | Formwork to slab decking (>10ft) hourdi | 2 CARPENTERS, 1 HELPER | 1.2 |  |  | - | -
21 | Formwork to slab decking (>10ft) hourdi | 2 CARPENTERS, 1 HELPER | 1 |  |  | - | -
22 | Formwork to staircase (non spiral) | 2 CARPENTERS, 1 HELPER | 0.4 |  |  | - | -
23 | Formwork to balcony parapets | 2 CARPENTERS, 1 HELPER | 0.6 |  |  | - | -
24 | Formwork to roof parapets | 2 CARPENTERS, 1 HELPER | 0.8 |  |  | - | -
25 | shutter Manufacture for pile caps | 1 CARPENTER + 1 HELPER | 2 |  |  | - | -
26 | shutter Fix for pile caps | 1 CARPENTER + 1 HELPER | 1.5 |  |  | - | -
27 | Deshutter footings/pile caps | 1 HELPER | 6 |  |  | - | -
28 | Shutter make column necks | 1 CARPENTER + 1 HELPER | 1.5 |  |  | - | -
29 | Shutter fix column necks | 1 CARPENTER + 1 HELPER | 1.2 |  |  | - | -
30 | Deshutter Column necks | 1 HELPER | 4.8 |  |  | - | -
31 | Shutter make tie beams | 1 CARPENTER + 1 HELPER | 1.2 |  |  | - | -
32 | shutter fix tie beams | 1 CARPENTER + 1 HELPER | 1 |  |  | - | -
33 | Column shutter making | 1 CARPENTER + 1 HELPER | 1.2 |  |  | - | -
34 | Column shutter fixing | 1 CARPENTER + 1 HELPER | 1 |  |  | - | -
35 | Column deshuttering | 1 HELPER | 4 |  |  | - | -
36 | Walls shutter making | 1 CARPENTER + 1 HELPER | 1.5 |  |  | - | -
37 | Walls shutter fixing | 1 CARPENTER + 1 HELPER | 0.8 |  |  | - | -
38 | De shutter Tie beam shutter | 1 HELPER | 4 |  |  | - | -
39 | Wall formwork deshuttering | 1 HELPER | 3.2 |  |  | - | -
40 | Staircase formwork making | 1 CARPENTER + 1 HELPER | 0.8 |  |  | - | -
41 | staircase formwork fixing | 1 CARPENTER + 1 HELPER | 0.8 |  |  | - | -
42 | Staircase formwork deshuttering | 1 HELPER | 1.6 |  |  | - | -
43 | Drop beams formwork making | 1 CARPENTER + 1 HELPER | 1 |  |  | - | -
44 | Drop beams formwork fixing | 1 CARPENTER + 1 HELPER | 0.8 |  |  | - | -
45 | Drop beams formwork stipping | 1 HELPER | 3.2 |  |  | - | -
46 | suspended slab formwork fixing | 1 CARPENTER + 1 HELPER | 1.2 |  |  | - | -
47 | suspended slab formwork deshutter | 1 HELPER | 5 |  |  | - | -
48 | Formwork fixing for sunshades | 1 CARPENTER + 1 HELPER | 0.7 |  |  | - | -
49 | Parapet formwork making | 1 CARPENTER + 1 HELPER | 1.2 |  |  | - | -
50 | Parapets formwork fixing | 1 CARPENTER + 1 HELPER | 1 |  |  | - | -
51 | Parapets formwork stripping | 1 HELPER | 4 |  |  | - | -
52 | Fixing of lintle formwork | 1 CARPENTER + 1 HELPER | 0.5 |  |  | - | -
53 | Fixing of lintle formwork | 1 CARPENTER + 1 HELPER | 0.5 |  |  | - | -
54 | Deshutter lintle formwork | 1 HELPER | 2 |  |  | - | -
55 | Deck formwork fixing | 1 CARPENTER + 1 HELPER | 1.5 |  |  | - | -
56 | Deck Formwork deshuttering | 1 HELPER | 6 |  |  | - | -
57 | Pipe scaffolding erection for slab | 1 SCAFFOLDER | 0.85 |  |  | - | -
58 | inverted beam shutter fixing | 1 CARPENTER + 1 HELPER | 1 |  |  | - | -
59 | De-Shuttering Manholes, square - circular (Timber) | 1 CARPENTER + 1 HELPER | 4 |  |  | - | -
60 | Manhole Shutter erection - square or circular(Timber) | 1 CARPENTER + 1 HELPER | 1.5 |  |  | - | -
61 | Metal Shutter for Manholes | 1 CARPENTER + 1 HELPER | 1 |  |  | - | -
62 | Metal Shutter for Precast Beams | 2 CARPENTERS + 2 HELPERS | 3 |  |  | - | -
63 | Metal Shutter for Pile caps | 2 CARPENTERS + 2 HELPERS | 3 |  |  | - | -
64 | Metal Shutters for Pile cap Beams | 2 CARPENTERS + 2 HELPERS | 3 |  |  | - | -
| Total |  |  |  |  | 0 | 0
D | DEPTH
U. GR | UNDERGROUND
D/S | DECK - SLAB
> | GREATER THAN
< | LESS THAN

## Masonry
Manpower Calculator- Masonry Works
Sr No. | Formwork Item | Unit of Measurement | Crew Size | Output in unit/hr | Enter Qty for the day in unit | Enter Working Hours per Day | Manpower required for the Day
[7 empty] | Carpenter | Mason | Helper
CERAMIC WORKS
1 | Ceramic skirting by glue | m | 1 MASON, 1 HELPER | 2.5 |  |  | - | - | -
2 | Ceramic skirting by glue to halls, corridors | m | 1 MASON, 1 HELPER | 3 |  |  | - | - | -
TILING WORKS
1 | Mosiac / Terrazo tiles to roofs | sqm | 1 MASON, 1 HELPER | 1.6 |  |  | - | - | -
2 | Mosiac / Terrazo tiles to floors | sqm | 1 MASON, 1 HELPER | 1.4 |  |  | - | - | -
3 | Mosiac skirting to halls | m | 1 MASON, 1 HELPER | 2.5 |  |  | - | - | -
4 | Mosiac skirting flush / recessed | m | 1 MASON, 1 HELPER | 1.4 |  |  | - | - | -
5 | Grouting / sealing to roof / floor tiles | m | 1 HELPER | 2.5 |  |  | - | - | -
KERBING / BLOCK PAVING WORKS
1 | P.C.C. Curve kerb base (to curves) | m | 1 MASON, 1 HELPER | 2.5 |  |  | - | - | -
2 | PCC to kerb base (Straight line) | m | 1 MASON, 1 HELPER | 3 |  |  | - | - | -
3 | Haunching to kerb base (Dumpes) | m | 1 MASON, 1 HELPER | 4 |  |  | - | - | -
4 | kerbstonse (Without PCC) | m | 1 MASON, 1 HELPER | 1.5 |  |  | - | - | -
5 | Interlock paving on pre prepared sub - base | sqm | 1 MASON, 1 HELPER | 0.2 |  |  | - | - | -
6 | Screed works including preparation | sqm | 1 MASON, 1 HELPER | 1.5 |  |  | - | - | -
7 | Haunching ot Kerb Base (Mixing Truck) | m | 1 MASON, 1 HELPER | 10 |  |  | - | - | -
MANHOLE/ DRAINAGE CONSTRUCTION
1 | Excavation for drains / manholes | cm | 1 HELPER | 0.5 |  |  | - | - | -
2 | Backfill to drains / manholes | cm | 1 HELPER | 0.1 |  |  | - | - | -
3 | Blockwork to manholes | Nos. | 1 MASON, 1 HELPER | 0.2 |  |  | - | - | -
4 | Plaster to manholes | Nos. | 1 MASON, 1 HELPER | 0.2 |  |  | - | - | -
5 | Benching to manholes | Nos. | 1 MASON, 1 HELPER | 0.4 |  |  | - | - | -
6 | Fix covers to manholes | Nos. | 1 MASON, 1 HELPER | 0.2 |  |  | - | - | -
7 | Fix gulley traps | Nos. | 1 MASON, 1 HELPER | 0.1 |  |  | - | - | -
8 | Laying of P.V.C. sleeves 4" - 12" | m | 4 HELPER | 24 |  |  | - | - | -
MISCELLANEOUS LABOUR WORKS
1 | Bitumen paint to concrete blockwork surfaces | sqm | 1 HELPER | 4 |  |  | - | - | -
2 | Bitumin painting Bases / piles | sqm | 1 HELPER | 7 |  |  | - | - | -
3 | Hacking of concrete surfaces | sqm | 1 HELPER | 5 |  |  | - | - | -
4 | fixing of flexcell sheets | sqm | 1 HELPER | 0.6 |  |  | - | - | -
5 | pile cutting/dressing | Nos. | 1 HELPER | 0.1 |  |  | - | - | -
6 | pile cutting/dressing (small diameter) | Nos. | 1 HELPER | 0.2 |  |  | - | - | -
7 | Vertical sealant (12 mm) | m | 1 HELPER | 2.5 |  |  | - | - | -
8 | Horizontal sealant (12 mm) | m | 1 HELPER | 5 |  |  | - | - | -
9 | Roof preparation for lw concrete | sqm | 1 MASON, 1 HELPER | 5 |  |  | - | - | -
10 | Angle fillet fixing | m | 1 MASON, 1 HELPER | 4 |  |  | - | - | -
11 | Hourdi block shifting and fixing to slab | Nos. | 2 HELPER | 20 |  |  | - | - | -
12 | Polythene sheet fixing | sqm | 1 HELPER | 3 |  |  | - | - | -
13 | Shaping of Soil Blinding | m | 1 MASON + 1 HELPER | 1 |  |  | - | - | -
14 | Protection Board installation | sqm | 1 CARPENTER + 1 HELPER | 8 |  |  | - | - | -
MISCELLANEOUS CARPENTARY WORKS
1 | A/C subframe manufacture / fixing | Nos. | 1 CARPENTER | 0.5 |  |  | - | - | -
2 | Door subframe manufacture / fixing | Nos. | 1 CARPENTER | 0.4 |  |  | - | - | -
3 | Water bar fixing | m | 1 CARPENTER | 2 |  |  | - | - | -
| Total | [5 empty] | 0 | 0 | 0

## Concreting
Manpower Calculator- Concreting Works
Sr No. | Formwork Item | Unit of Measurement | Crew Size | Output in unit/hr | Enter Qty for the day in unit | Enter Working Hours per Day | Manpower required for the Day
[7 empty] | Carpenter | Mason | Helper
1 | Ceramic skirting by glue | m | 1 MASON, 1 HELPER | 2.5 |  |  | - | - | -
2 | Standard rate 1 man | cum |  | 1 |  |  | - | - | -
3 | Concrete to PCC blinding (100 mm thick) | cum | 1 MASON, 10 HELPERS | 2.7 |  |  | - | - | -
4 | Concrete to slabs/beams, by pump | cum | 6 MASONS, 18 HELPERS, 1 CARPENTER | 18 |  |  | - | - | -
5 | Concrete to slabs / beams by crane | cum | 1 MASON, 6 HELPERS, 0.5 OPERATOR | 2.7 |  |  | - | - | -
6 | Concrete to walls / columns, by pump | cum | 4 MASONS, 16 HELPERS, 2 CARPENTERS | 8.1 |  |  | - | - | -
7 | Concrete by site mix | cum | 1 MASON, 12 HELPERS , 0.5 CARPENTER | 0.9 |  |  | - | - | -
8 | Concrete Columns | cum | 8 HELPERS | 1 |  |  | - | - | -
9 | Concrete suspended slab (pump) | cum | 3 MASONS + 6 HELPERS | 15 |  |  | - | - | -
10 | Concrete parapets/staircases | cum | 8 HELPERS | 0.7 |  |  | - | - | -
11 | Blinding concrete 50 mm (readymix) | cum | 1 MASON + 4 HELPER | 8 |  |  | - | - | -
12 | Blinding concrete 50 mm (sitemix) | cum | 1 MASON + 8 HELPER | 1 |  |  | - | - | -
13 | Concrete footings & pile caps | cum | 1 MASON + 4 HELPER | 12 |  |  | - | - | -
14 | Concrete tiebeams, ground beams | cum | 1 MASON + 5 HELPER | 6 |  |  | - | - | -
15 | Concrete column necks | cum | 8 HELPER | 1.5 |  |  | - | - | -
16 | Concrete Ground slab | cum | 3 MASONS + 6 HELPER | 1.5 |  |  | - | - | -
17 | Concrete to precast slabs, beams | cum | 2 MASONS + 1 HELPER | 3 |  |  | - | - | -
GENERAL LABOUR WORKS
1 | Unloading reinforcement ((Flat Bed Truck) | Nos | 4 HELPERS | 0.2 |  |  | - | - | -
2 | Loading reinforcement to slab (With Crane) | Nos | 4 HELPERS (Flat Bed Truck loads) | 0.2 |  |  | - | - | -
3 | Loading blockwork to site (with Wheel Burrow) | Nos | 1 HELPER | 40 |  |  | - | - | -
4 | Loading mortar to site location | [5 empty] | - | - | -
5 | Mixing mortar for distribution 0, 3 L mixer | cum | 4 HELPER | 0.6 |  |  | - | - | -
6 | Site mixing of ready mix for distribution Hand mix | cum |  | 0.3 |  |  | - | - | -
7 | Loading ready mix to site location | [5 empty] | - | - | -
| NON TARGET RELATED ACTIVITES | [5 empty] | - | - | -
1 | Stacking of formwork |  | 2 HELPERS |  |  |  | - | - | -
2 | Curing of Substructure works |  | 2 HELPERS |  |  |  | - | - | -
3 | Curing of beams / slabs Hessiant Water |  | 2 HELPERS |  |  |  | - | - | -
4 | Curing of columns (Hessiant Water) | m | 1 MASON + 2 HELPERS | 3.6 |  |  | - | - | -
5 | Builders work make good chases | [5 empty] | - | - | -
6 | Site cleaning | sqm | 1 HELPER | 25 |  |  | - | - | -
7 | Repairs to finished works | sqm | 1 MASON | 1 |  |  | - | - | -
| Total | [5 empty] | 0 | 0 | 0
Item No. |  |  | CREW SIZE | NON MEASURABLE
1 | Maintenance of site services |  | 2 HELPERS
2 | Operators for mixers |  | 2/MIXER
3 | Operators for compaction equipment |  | 1 UNIT
4 | Office boy |  | ARABTEC 1 / CONSULTANT 1
5 | Watchman |  | 2 MIN
6 | Storekeeper |  | 1/SHIFT
Page 6 of 7

## Reinforcement
Manpower Calculator- Reinforcement Works
Sr No. | Formwork Item | Unit of Measurement | Crew Size | Output in unit/hr | Enter Qty for the day in unit | Enter Working Hours per Day | Manpower required for the Day
[7 empty] | Barbinder | Mason | Helper
Reinforcement Fixing For Rebar dia < 16mm
1 | Fix Rebar to footings & tie beams | kg | 2 STEEL FIXER | 25 |  |  | - | - | -
2 | Fix Rebar to walls, columns, beams, solid slabs | kg | 1 STEEL FIXER | 20 |  |  | - | - | -
3 | Fix rebar to ribs of hourdi slab | kg | 1 STEEL FIXER | 18 |  |  | - | - | -
4 | Fix rebar to mesh reinforcement | kg | 1 STEEL FIXER | 15 |  |  | - | - | -
5 | Fix rebar to hidden beams | kg | 1 STEEL FIXER | 20 |  |  | - | - | -
Reinforcement Fixing For Rebar dia > 16mm
1 | Fix Rebar to footings & tie beams | kg | 1 STEEL FIXER | 78 |  |  | - | - | -
2 | Fix Rebar to walls, columns, beams, solid slabs | kg | 1 STEEL FIXER | 38 |  |  | - | - | -
3 | Fix rebar to ribs of hourdi slab | kg | 1 STEEL FIXER | 35 |  |  | - | - | -
4 | Fix rebar to mesh reinforcement | kg | 1 STEEL FIXER | 15 |  |  | - | - | -
5 | Fix rebar to hidden beams | kg | 1 STEEL FIXER |  |  |  | - | - | -
Reinforcement Cutting
1 | Steel cutting and bending 18.25 mm | kg | 1 STEEL FIXER | 50 |  |  | - | - | -
2 | Steel cutting and bending 8 - 16 mm | kg | 1 STEEL FIXER | 40 |  |  | - | - | -
EXCAVATION
1 | Manual Excavation | cum | 1 HELPER | 0.3 |  |  | - | - | -
2 | Backfill + levelling | cum | 1HELPER | 0.5 |  |  | - | - | -
3 | Shaping of sloped earth for blinding for bases including compaction | sqm | 1 MASON + 2 HELPER | 0.6 |  |  | - | - | -
| Total | [5 empty] | 0 | 0 | 0

## Block work-Plaster
Manpower Calculator- Blockwork & Plaster Works
Sr No. | Formwork Item | Unit of Measurement | Crew Size | Output in unit/hr | Enter Qty for the day in unit | Enter Working Hours per Day | Manpower required for the Day
[7 empty] | Mason | Helper
MASONARY WORKS
1 | Hollow Blockwork (100, 150 & 200 mm) | No. | 1 MASON, 1 HELPER | 12 |  |  | - | -
2 | Hollow Blockwork (large panels) | No. | 1 MASON, 1 HELPER | 14 |  |  | - | -
3 | Solid blockwork | No. | 1 MASON, 1 HELPER | 9.5 |  |  | - | -
4 | Solid Blockwork as Raft forms | No. | 1 MASON, 1 HELPER | 11 |  |  | - | -
PLASTERWORK
1 | Plaster (internal), walls final coat | sqm | 1 MASON, 1 HELPER | 16 |  |  | - | -
2 | Plaster (internal), walls rush coat | sqm | 2 HELPER | 15 |  |  | - | -
3 | Plaster (internal), walls mesh | sqm | 1 HELPER | 10 |  |  | - | -
4 | Plaster (internal), walls hacking | sqm | 1 HELPER | 10 |  |  | - | -
5 | Plaster (internal), walls guide point | sqm | 1 MASON, 1 HELPER | 10 |  |  | - | -
6 | Plaster (internal), walls corner beads | sqm | 1 MASON, 1 HELPER | 10 |  |  | - | -
7 | Plaster (external), walls with grooves | sqm | 1 MASON, 1 HELPER | 10 |  |  | - | -
8 | Plaster (external), walls without grooves | sqm | 1 MASON, 1 HELPER | 1.2 |  |  | - | -
9 | Plaster (external), walls rush coat | sqm | 2 HELPER | 15 |  |  | - | -
10 | Plaster (external), walls mesh | sqm | 1 HELPER | 10 |  |  | - | -
11 | Plaster (external), walls hacking | sqm | 1 HELPER | 10 |  |  | - | -
12 | Plaster (external), walls guide points | sqm | 1 MASON, 1 HELPER | 10 |  |  | - | -
13 | Plaster (external), walls corner beads | sqm | 1 MASON, 1 HELPER | 10 |  |  | - | -
14 | Plastering of Arches/Mullians | sqm | 1 MASON, 1 HELPER | 8 |  |  | - | -
15 | Floor screed 50mm thick | sqm | 1 MASON, 1 HELPER | 2 |  |  | - | -
16 | Roof screed 100 mm thick | sqm | 1 MASON, 1 HELPER | 1.5 |  |  | - | -
17 | Mosiac floor Tiles fixing | sqm | 1 MASON, 1 HELPER | 1.6 |  |  | - | -
18 | Floor Screed 25mm thick | sqm | 1 Mason + 1 Helper | 0.6 |  |  | - | -
| CERAMIC WORKS | [5 empty] | - | -
1 | Ceramic tiles to walls by mortar | sqm | 1 MASON, 1 HELPER | 0.8 |  |  | - | -
2 | Ceramic tiles to walls, mortar to corridors | sqm | 1 MASON, 1 HELPER | 0.9 |  |  | - | -
3 | Ceramic tiles to walls, cut pieces | sqm | 1 MASON | 2 |  |  | - | -
4 | Ceramic tiles to walls grouting | sqm | 1 HELPER | 5 |  |  | - | -
5 | Ceramic tiles to walls, by glue | sqm | 1 MASON, 1 HELPER | 1.2 |  |  | - | -
6 | Ceramic tiles to walls, corridors, by glue | sqm | 1 MASON, 1 HELPER | 1.3 |  |  | - | -
7 | Ceramic tiles to walls, by glue, cut pieces | sqm | 1 MASON | 2 |  |  | - | -
8 | Ceramic tiles to walls, by glue, grouting | sqm | 1HELPER | 5 |  |  | - | -
9 | Ceramic tiles to floors | sqm | 1 MASON, 1 HELPER | 1 |  |  | - | -
10 | Ceramic tiles to floors in halls | sqm | 1 MASON, 1 HELPER | 1.2 |  |  | - | -
11 | Ceramic tiles to floors, cut pieces | sqm | 1 MASON | 2 |  |  | - | -
12 | Ceramic tiles to floors, grouting | sqm | 1 HELPER | 5 |  |  | - | -
13 | Marble flooring | sqm | 1 MASON + 1 HELPER | 0.6 |  |  | - | -
14 | Ceramic tiles to floors, cut pieces | sqm | 1 MASON | 2 |  |  | - | -
15 | Ceramic tiles to floors, grouting | sqm | 1 HELPER | 5 |  |  | - | -
16 | Marble flooring | sqm | 1 MASON + 1 HELPER | 6 |  |  | - | -
| Total | [5 empty] | 0 | 0

## Tiling
Manpower Calculator- Reinforcement Works
Sr. No. | Size of Tile (cm x cm) | Area | Unit of Measurement | Crew Size | Output in sqm/hr | Enter Qty for the day in sqm | Enter Working Hours per Day | Manpower required for the Day
[8 empty] | Mason | Helper
1 | 30 X 30 | Kitchen- Floor | sqm | 1 Mason, 1 Helper | 1.4 |  |  | - | -
2 | 30 X 30 | Corridor- Floor with pattern | sqm | 2 Masons, 1 Helper | 1 |  |  | - | -
3 | 40 X 40 | Bedroom- Floor | sqm | 1 Mason, 1 Helper | 2.3 |  |  | - | -
4 | 20 X 20 | Store (small area)- Floor | sqm | 1 Mason, 1 Helper | 1 |  |  | - | -
5 | 30 X 60 | Bathroom- Floor | sqm | 2 Mason, 1 Helper | 0.6 |  |  | - | -
6 | 30 X 30 | Bathroom- Floor + Wall | sqm | 2 Mason, 1 Helper | 0.5 |  |  | - | -
7 | 10 X 10 | Kitchen- Wall | sqm | 1 Mason, 1 Helper | 0.85 |  |  | - | -
8 | 30 X 60 | Corridor- Wall | sqm | 1 Mason, 1 Helper | 1.45 |  |  | - | -
9 | 30 X 30 | Bathroom- Wall | sqm | 2 Mason, 1 Helper | 0.7 |  |  | - | -
|  | Total | [5 empty] | 0 | 0